## Sheet1
Sprint Week | Module/Component | Task Description | Assigned Role | Estimated Days | Expected Artifacts
Week 1 | Planning & Scope | Define system requirements, map financial query types, and detail success metrics. | Project Lead / Analyst | 2 | Scope Doc & Definition Criteria
Week 1 | Data Engineering | Generate synthetic balance sheets and structured corporate annual reports. | Data Engineer | 3 | Mock PDFs & Raw JSON Data Tables
Week 2 | RAG Pipeline Setup | Implement Text Splitters, define ChromaDB/FAISS vector collections, embed data. | AI Engineer | 4 | Vector Store Ingestion Script
Week 2 | Base Agent Setup | Create baseline LLM chains with explicit system prompts for financial text parsing. | AI Engineer | 3 | Isolated Agent Python Modules
Week 3 | Multi-Agent Orchestration | Configure LangGraph state machine linking Retrieval, KPI Extraction, & Summary agents. | AI Engineer | 4 | State Graph Workflow Script
Week 3 | Frontend Development | Construct interactive Streamlit dashboard mapping state outputs and file uploads. | Frontend Developer | 3 | Streamlit UI App Code (app.py)
Week 4 | Cloud Deployment | Launch AWS EC2 instance, provision S3 buckets for PDFs, set up security groups. | DevOps / AIOps Engineer | 3 | Live Web URL & AWS Config Proofs
Week 4 | Testing & Packaging | Perform evaluation runs on KPIs, build presentation slides, record demo walkthrough. | All Team Members | 4 | ZIP Package / Drive Link Submission